## Sheet1
Strategic Community Management: Project Plan Template | Hours |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
|  | Assigned | Mon | Tues | Weds | Thurs | Fri | Sat | Sun | Mon | Tues | Weds | Thurs | Fri | Sat | Sun | Mon | Tues | Weds | Thurs | Fri | Sat | Sun | Mon | Tues | Weds | Thurs | Fri | Sat | Sun | Mon | Tues | Weds | Thurs | Fri | Sat | Sun | Mon | Tues | Weds | Thurs | Fri | Sat | Sun | Mon | Tues | Weds | Thurs | Fri | Sat | Sun | Mon | Tues | Weds | Thurs | Fri | Sat | Sun | Mon | Tues | Weds | Thurs | Fri | Sat | Sun | Mon | Tues | Weds | Thurs | Fri | Sat | Sun | Mon | Tues | Weds | Thurs | Fri | Sat | Sun | Mon | Tues | Weds | Thurs | Fri | Sat | Sun
Find experts | 20
Decide who qualifies as an expert | 6
Create a list of contacts for potential experts interviews | 4
Schedule calls with expert and identify those with something interesting to say | 10
Ensure high-quality advice | 6
Clarify the key points the experts will make | 2
Clarify questions to ensure it’s most relevant to the audience. | 2
Checking timing | 2
Great Medium | 16
Find and book a filming studio for the expert interview | 4
Arrange travel for the expert | 2
Book a photographer for imagery | 2
Hire a designer to help design the intro slides | 3
Book an editor with availability to edit the video | 4
Select a hosting platform | 1
Big Audience | 25
Write an email series to promote the expert | 6
Arrange for other sites to cover the takeaways | 4
Creating a digest of key points | 3
Setup a reward scheme for referrals | 4
Paid advertising | 8